## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Learn basic Java concepts like OOP, collections, and exceptions | M | NA | Intern | Completed
Sprint 1 | Sprint 1 | US-02 | Create a simple CRUD app using Java | M | US-01 | Intern | Completed
Sprint 1 | Sprint 1 | US-03 | Set up project with required tools and dependencies | M | US-02 | Intern | Completed
Sprint 1 | Sprint 1 | US-04 | Design database for users, accounts, and transactions | M | US-03 | Intern | Completed
Sprint 1 | Sprint 1 | US-05 | Create user registration with validation | M | US-04 | Intern | Completed
Sprint 2 | Sprint 2 | US-06 | Add OTP verification during registration | M | US-05 | Intern | Completed
Sprint 2 | Sprint 2 | US-07 | Create login API with token | M | US-05 | Intern | Completed
Sprint 2 | Sprint 2 | US-08 | Add forgot password feature using email | M | US-07 | Intern | Completed
Sprint 2 | Sprint 2 | US-09 | Allow users to reset password using token | M | US-08 | Intern | Completed
Sprint 2 | Sprint 2 | US-10 | Implement account creation API linked to registered user | M | US-07 | Intern | Completed
Sprint 2 | Sprint 2 | US-11 | Implement get account by account number API | M | US-10 | Intern | Completed
Sprint 2 | Sprint 2 | US-12 | Implement deposit and withdrawal APIs with balance updates | M | US-10 | Intern | Completed
Sprint 2 | Sprint 2 | US-13 | Implement fund transfer API between accounts with validation | M | US-12 | Intern | Completed
Sprint 2 | Sprint 2 | US-14 | Implement transaction history API and CSV statement download | S | US-12 | Intern | Completed
Sprint 2 | Sprint 2 | US-15 | Implement admin login, forgot password, and reset password APIs | M | US-07 | Intern | Completed
Sprint 3 | Sprint 3 | US-16 | Implement admin API to list all accounts with search/filter support | M | US-15 | Intern | Completed
Sprint 3 | Sprint 3 | US-17 | Implement admin freeze and unfreeze account status API | M | US-15 | Intern | Completed
Sprint 3 | Sprint 3 | US-18 | Add optional low-balance email alert service | C | US-12 | Intern | Completed
Sprint 3 | Sprint 3 | US-19 | Enable CORS on all REST endpoints for frontend integration | M | US-05 | Intern | Completed
Sprint 3 | Sprint 3 | US-20 | Build React + Vite project structure and set up routing | M | US-19 | Intern | Completed
Sprint 3 | Sprint 3 | US-21 | Develop home, registration, OTP send/verify, and login pages | M | US-20 | Intern | Completed
Sprint 3 | Sprint 3 | US-22 | Develop forgot password and reset password pages | M | US-20 | Intern | Completed
Sprint 3 | Sprint 3 | US-23 | Develop user dashboard with deposit, withdraw, transfer, and statement download | M | US-20 | Intern | Completed
Sprint 3 | Sprint 3 | US-24 | Develop admin dashboard with account listing, search, freeze/unfreeze actions | M | US-20 | Intern | Completed
Sprint 3 | Sprint 3 | US-25 | Add session persistence using localStorage and route protection for user/admin pages | S | US-21 | Intern | Completed
Sprint 3 | Sprint 3 | US-26 | Perform end-to-end testing, fix bugs, and finalize the application | M | US-21 | Intern | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T-01 | Study Java OOP concepts – classes, inheritance, interfaces | 23-Feb-2026 | 24-Feb-2026 | Intern | Learning | Completed | 3 | Day 1: 1.5; Day 2: 1.5
US-01 | T-02 | Practice Java collections – ArrayList, HashMap, and iterators | 24-Feb-2026 | 25-Feb-2026 | Intern | Learning | Completed | 2 | Day 1: 2
US-01 | T-03 | Practice Java exception handling with custom exceptions | 25-Feb-2026 | 25-Feb-2026 | Intern | Learning | Completed | 1.5 | Day 1: 1.5
US-02 | T-04 | Design a simple CRUD app (Student records) with in-memory list | 26-Feb-2026 | 26-Feb-2026 | Intern | Development | Completed | 3 | Day 1: 3
US-02 | T-05 | Add create, read, update, delete operations to the CRUD app | 26-Feb-2026 | 27-Feb-2026 | Intern | Development | Completed | 2.5 | Day 1: 1.2; Day 2: 1.2
US-03 | T-06 | Create Maven project and add Spark Java, Gson, MySQL driver dependencies | 02-Mar-2026 | 02-Mar-2026 | Intern | Setup | Completed | 2 | Day 1: 2
US-03 | T-07 | Set up Spark Java main server class with a test GET endpoint | 02-Mar-2026 | 03-Mar-2026 | Intern | Development | Completed | 2 | Day 1: 2
US-04 | T-08 | Design users, accounts, and transactions tables in MySQL | 03-Mar-2026 | 03-Mar-2026 | Intern | Design | Completed | 2.5 | Day 1: 2.5
US-04 | T-09 | Write SQL scripts to create schema and test with sample data | 04-Mar-2026 | 04-Mar-2026 | Intern | Development | Completed | 1.5 | Day 1: 1.5
US-05 | T-10 | Create User model class and UserRepository with JDBC connection | 04-Mar-2026 | 05-Mar-2026 | Intern | Development | Completed | 3 | Day 1: 1.5; Day 2: 1.5
US-05 | T-11 | Implement POST /register API with validation and DB insert | 05-Mar-2026 | 06-Mar-2026 | Intern | Development | Completed | 3 | Day 1: 1.5; Day 2: 1.5
SPRINT 2 BACKLOG
US-06 | T-12 | Integrate Jakarta Mail to send OTP emails on registration | 09-Mar-2026 | 09-Mar-2026 | Intern | Development | Completed | 3 | Day 1: 3
US-06 | T-13 | Implement POST /verify-otp API to validate OTP and activate account | 09-Mar-2026 | 10-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 1.2; Day 2: 1.2
US-07 | T-14 | Implement POST /login API with credential check and token response | 10-Mar-2026 | 10-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 2.5
US-08 | T-15 | Implement POST /forgot-password API – generate and email reset link | 11-Mar-2026 | 11-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 2.5
US-09 | T-16 | Implement POST /reset-password API – validate token and update password | 11-Mar-2026 | 12-Mar-2026 | Intern | Development | Completed | 2 | bar: Day 1 to Day 2
US-10 | T-17 | Implement POST /accounts API to create a bank account for a user | 12-Mar-2026 | 12-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 2.5
US-11 | T-18 | Implement GET /accounts/{id} to retrieve account details | 13-Mar-2026 | 13-Mar-2026 | Intern | Development | Completed | 1.5 | Day 1: 1.5
US-12 | T-19 | Implement POST /deposit and POST /withdraw APIs with balance update | 13-Mar-2026 | 14-Mar-2026 | Intern | Development | Completed | 3 | Day 1: 1.5; Day 2: 1.5
US-13 | T-20 | Implement POST /transfer API with sender, receiver, and amount validation | 16-Mar-2026 | 16-Mar-2026 | Intern | Development | Completed | 3.5 | Day 1: 3.5
US-14 | T-21 | Implement GET /transactions API to retrieve transaction history | 17-Mar-2026 | 17-Mar-2026 | Intern | Development | Completed | 2 | Day 1: 2
US-14 | T-22 | Add CSV export of transaction statement using GET /transactions/download | 17-Mar-2026 | 18-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 1.2; Day 2: 1.2
US-15 | T-23 | Implement admin login API POST /admin/login | 18-Mar-2026 | 18-Mar-2026 | Intern | Development | Completed | 2 | Day 1: 2
US-15 | T-24 | Implement admin forgot-password and reset-password APIs | 19-Mar-2026 | 20-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 1.2; Day 2: 1.2
SPRINT 3 BACKLOG
US-16 | T-25 | Implement GET /admin/accounts API to list all accounts | 23-Mar-2026 | 23-Mar-2026 | Intern | Development | Completed | 2 | Day 1: 2
US-17 | T-26 | Implement PATCH /admin/accounts/{id}/freeze and /unfreeze APIs | 23-Mar-2026 | 24-Mar-2026 | Intern | Development | Completed | 2 | bar: Day 1 to Day 2
US-18 | T-27 | Implement low-balance email alert in deposit/withdraw logic | 24-Mar-2026 | 24-Mar-2026 | Intern | Development | Completed | 2 | Day 1: 2
US-19 | T-28 | Add CORS filter to Spark server to allow React dev origin | 24-Mar-2026 | 25-Mar-2026 | Intern | Development | Completed | 1.5 | Day 1: 0.8; Day 2: 0.7
US-20 | T-29 | Set up React + Vite project and configure React Router for all pages | 25-Mar-2026 | 25-Mar-2026 | Intern | Setup | Completed | 2 | Day 1: 2
US-21 | T-30 | Build Home page and User Registration form with OTP send flow | 25-Mar-2026 | 26-Mar-2026 | Intern | Development | Completed | 3 | Day 1: 1.5; Day 2: 1.5
US-21 | T-31 | Build OTP verify page and User Login page | 26-Mar-2026 | 26-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 2.5
US-22 | T-32 | Build Forgot Password and Reset Password pages for users | 27-Mar-2026 | 27-Mar-2026 | Intern | Development | Completed | 2 | Day 1: 2
US-23 | T-33 | Build User Dashboard with account overview and action buttons | 27-Mar-2026 | 27-Mar-2026 | Intern | Development | Completed | 3 | Day 1: 3
US-23 | T-34 | Implement Deposit, Withdraw, Transfer forms and API calls in React | 28-Mar-2026 | 28-Mar-2026 | Intern | Development | Completed | 3.5 | Day 1: 3.5
US-23 | T-35 | Add transaction history view and statement download button | 28-Mar-2026 | 28-Mar-2026 | Intern | Development | Completed | 2 | Day 1: 2
US-24 | T-36 | Build Admin Login, Forgot Password, and Reset Password pages | 28-Mar-2026 | 29-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 1.2; Day 2: 1.2
US-24 | T-37 | Build Admin Dashboard with account listing, search, and filter | 29-Mar-2026 | 29-Mar-2026 | Intern | Development | Completed | 3 | Day 1: 3
US-24 | T-38 | Add freeze and unfreeze action buttons in admin dashboard | 29-Mar-2026 | 30-Mar-2026 | Intern | Development | Completed | 2 | bar: Day 1 to Day 2
US-25 | T-39 | Add localStorage session persistence and protected route logic | 30-Mar-2026 | 30-Mar-2026 | Intern | Development | Completed | 2.5 | Day 1: 2.5
US-26 | T-40 | Perform end-to-end manual testing across all user and admin flows | 30-Mar-2026 | 30-Mar-2026 | Intern | Testing | Completed | 3 | Day 1: 3
US-26 | T-41 | Fix identified bugs and do final UI polish | 30-Mar-2026 | 30-Mar-2026 | Intern | Bug Fix | Completed | 2 | Day 1: 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Mon, 23-Feb-2026 | None – team started Java basics practice | Began with Java OOP, covered classes and inheritance
Sprint 1 | Tue, 24-Feb-2026 | Slight confusion around interface vs abstract class | Resolved with quick team discussion and examples
Sprint 1 | Wed, 25-Feb-2026 | None | Completed exception handling exercises
Sprint 1 | Thu, 26-Feb-2026 | None | Started simple CRUD app with Student records
Sprint 1 | Fri, 27-Feb-2026 | CRUD delete operation had logic error | Fixed the delete method and tested all operations
Sprint 1 | Mon, 02-Mar-2026 | Maven dependency resolution took time | Resolved by correcting pom.xml versions
Sprint 1 | Tue, 03-Mar-2026 | None | Set up Spark Java server with test GET endpoint
Sprint 1 | Wed, 04-Mar-2026 | MySQL connection string was incorrect initially | Fixed JDBC URL and verified DB connectivity
Sprint 1 | Thu, 05-Mar-2026 | None | Created User model and repository classes
Sprint 1 | Fri, 06-Mar-2026 | Validation logic for registration had edge cases | Added null checks and tested edge input cases
Sprint 2 | Mon, 09-Mar-2026 | Jakarta Mail SMTP config needed app password setup | Configured Gmail SMTP with app-specific password
Sprint 2 | Tue, 10-Mar-2026 | None | OTP verify and user login APIs completed
Sprint 2 | Wed, 11-Mar-2026 | Email reset link URL needed to match frontend route | Agreed on reset URL format across backend and frontend
Sprint 2 | Thu, 12-Mar-2026 | None | Account creation API implemented and tested
Sprint 2 | Fri, 13-Mar-2026 | None | Account retrieval and deposit/withdraw started
Sprint 2 | Mon, 16-Mar-2026 | Transfer API needed to handle insufficient funds gracefully | Added balance check and proper error response
Sprint 2 | Tue, 17-Mar-2026 | None | Transaction history API done
Sprint 2 | Wed, 18-Mar-2026 | CSV download headers needed to be set correctly | Added Content-Disposition header to the response
Sprint 2 | Thu, 19-Mar-2026 | Admin login endpoint conflicted with user login route naming | Renamed admin routes to /admin/login etc.
Sprint 2 | Fri, 20-Mar-2026 | None | Admin forgot/reset password APIs completed
Sprint 3 | Mon, 23-Mar-2026 | None | Admin account listing API done, started freeze/unfreeze
Sprint 3 | Tue, 24-Mar-2026 | CORS blocking React dev server requests | Added CORS headers to all responses in Spark server
Sprint 3 | Wed, 25-Mar-2026 | Vite proxy config needed for localhost:8080 routing | Added proxy config in vite.config.js
Sprint 3 | Thu, 26-Mar-2026 | None | Registration and OTP pages working end-to-end
Sprint 3 | Fri, 27-Mar-2026 | None | Login, forgot/reset password, and dashboard pages completed
Sprint 3 | Mon, 30-Mar-2026 | Protected routes weren't redirecting on page refresh | Fixed by reading session from localStorage on mount

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 23-Feb-2026 | 06-Mar-2026 | Intern | Start writing task notes at the end of each session | Stop spending too long on syntax details – use docs instead | Continue daily code review habit | Created a quick-reference cheat sheet for Java syntax
2 | Sprint 2 | 09-Mar-2026 | 20-Mar-2026 | Intern | Start testing each API endpoint with Postman right after implementation | Stop leaving API validation until the end of the sprint | Continue the practice of naming endpoints consistently | Added Postman collection shared within team for all endpoints
3 | Sprint 3 | 23-Mar-2026 | 30-Mar-2026 | Intern | Start planning component structure before writing React code | Stop making UI changes without checking backend response format first | Continue incremental integration – backend first, then connect frontend | Created a simple component diagram before building each new page
4
5
6
7